EEGECS – Working Group 1 (Undergraduate education)

Table of scheduled activities

(beginning from the General Assembly in 2002 December)

| YEAR | TASK | OUTPUT | DATE |
| --- | --- | --- | --- |
| 1st (2003) | Finishing the structure of the questionnaire. Consulting to determinate the structure of the national reports. | Questionnaire about the study plans | January |
|  | Study of the Tuning Project (responsible: Deusto University, Spain), to learn about methodologies for comparison of diplomas (September-October 2003) * |  | January-April |
|  | Delivering the questionnaire, gathering answers. Finishing the structure of the national reports. |  | February-March |
|  | Analysis of answers. Elaboration of national reports. Inclusion of the national reports in the EEGECS website. | National reports | April-July |
| 2nd (2003–2004) | WG1 meeting (three days) Workshop: - Analysis of national reports on study systems, degrees etc - Identify common elements and differences. - Start elaborating a methodology for comparing degrees in this discipline (take into account Tuning Project report). Identify obstacles and strengths to move to a two-tier degree system (3y BSc and 5y MSc) |  | September |
|  | Elaboration of a questionnaire about systems in other parts of the world ( USA…)** | Questionnaire about the study plans | September- December |
|  | Study of works, researches, experiences, etc about methodologies for comparing degrees in our fields. |  | September- November |
|  | Finalisation of methodology | Methodology for comparing degrees | December |
|  | Delivering the questionnaire, gathering answers. |  | January-February |
|  | Elaboration of brief report on structures at other parts of the world. | Report | March |
|  | Survey on groups reporting on curriculum development criteria for engineering studies and studies related to Geomatics, Cartography, Surveying… (FIG, CLG, Sefi, Feani and others). | List of groups to contact for information on curriculum development. | April |
|  | Contact those groups and elaborate reports. | Report on curriculum development criteria | May-July |
| 3nd (2004–2005) | Analyse the rest of reports of other WGs (Ways to include research into education; needs of the market (skills + lifelong learning+ research); languages, mobility and new subject; best pedagogical practices…) |  | September-October |
|  | WG1 meeting Presentation of all reports and discussion, exchange of ideas… definition of core curricula for different specialisations and a core curriculum (general). |  | November |
|  | Work individually and in co-operation with rest of WG1 via email, video-conferencing…, to design the core curricula determined in the meeting. |  | November-March |
|  | Finalise Core curricula general and for each specialisation. Write a set of recommendations for implementing the core curricula proposed |  | April-June |
|  | WG1 meeting (4 days in June) | Core curricula and recommendations | June |
|  | 2nd General Meeting of EEGECS - Overview of the projects results and outcomes. - Forum on further steps to continue progress work and provide a permanent platform (via the network, or using already existing structures like FIG, CLG…). - Decide on general dissemination activities and materials. - Discuss financial matters. |  | July |

Text with bold italic fonts represents a task planned originally in other date (this date is written after the task and within brackets)

Text with italic fonts represents open questions and tasks to be defined more exactly.

* It was brought forward to help us during the determination of the structure of the national reports.

** We should consider to use (as a starting point) the questionnaire prepared for European universities, completing it with other questions.

The dates indicated from the second year could change after our second meeting.